## Project Plan
Module | Task | Status | Completion Duration (Days)
1. Web APIs | Database Design & Architecture Setup | Completed | 2
1. Web APIs | Core & Shared Services | Completed | 2
1. Web APIs | Admin & Keeper APIs | Completed | 2
1. Web APIs | User & Journey Routing APIs | In Progress | 2
2. Admin Website | UI/UX Setup & Theming | Completed | 1
2. Admin Website | Data Grids & Management Screens | Completed | 2
2. Admin Website | Authentication & Analytics Dashboard | In Progress | 1
3. Keeper Website | Auth & Profile/Shop Onboarding | Completed | 1
3. Keeper Website | Offer Creation & Management Forms | Completed | 2
3. Keeper Website | Dashboard Analytics & Reviews | In Progress | 1
4. User Website | Core Setup, Theming & Auth | Completed | 2
4. User Website | Maps, Geocoding & Discover Features | In Progress | 3
4. User Website | Journey/Trip Planning & Navigation | In Progress | 2
4. User Website | User Profiles, History & Feed | Completed | 1
|  | Total Days: | 24